## Sheet1
No. | Risk Identified | Response Strategy | Risk Owner | Risk Owner |  |  | Status
1 | Integration | Compatibility Testing of all the | All the developers |  |  |  | Report the output of testing to
|  | integrated components | of the ecom website |  |  |  | Project Manager
2 | Scope | Redifining Scope |  |  | Nitesh Gupta |  | Take the Stakeholders into
|  | and Quality Requirements |  |  |  |  | account
3 | Time | Re-evaluate Project duration from |  |  | All Project Leaders | Members | Make requisite Changes to
|  | time to time and Schedule remaining |  |  |  |  | the Working strategy
activities accordingly
4 | Cost | Estimate Errors; Cut Expenditure; |  |  | Vinay Thapa |  | Team leaders should report to
|  | Reduce unnecessary breaks |  |  |  |  | the Finance Department
5 | Quality | Ensure Quality Assurance Program; |  |  | Vrattant Arora |  | Team Leaders should ensure
|  | verify from External institutions; |  |  |  |  | excellent Component quality
6 | Human Resource | Proper conflict management; Proper |  |  | Nimish Kochhar |  | Team leaders should ensure
|  | definition of responsibilities and |  |  |  |  | proper grievance addressal
leadership